## Slide 1
2022
2022
Today
Mar
Apr
2022
5 days
Mar 14 - Mar 18
Literature research & lit. review skeleton
Mar 18 - Mar 25
6 days
Literature review draft
Mar 28 - Apr 1
5 days
Final literature review
Apr 4 - Apr 14
9 days
Find small example RRBS data set
Apr 19 - Apr 22
Implement different classifiers and test on data
4 days
Apr 25 - Apr 29
5 days
Tranform lit. review to intro for dissertation
SICK
Apr 4 - Apr 10
5 days
MSc Research Project - Plan for March/April

## Slide 2
2022
2022
Today
Week 1
2
2022
3
4
5
May 2 - May 4
3 days
Find larger example RRBS data set
May 9 - May 13
Train different classifiers on mock data
5 days
May 9 - May 20
Optimisation of classifiers
10 days
Polish intro section
May 2 - May 6
5 days
Write methods section
May 10 - May 20
9 days
Run analysis on large mock data
May 9 - May 16
6 days
May 23 - May 31
Investigate & preprocess real data set
7 days
MSc Research Project - Plan for May