## Slide 1
2022
2022
Today
Mar
Apr
2022
5 days
Mar 14 - Mar 18
Literature research & lit. review skeleton
Mar 18 - Mar 25
6 days
Literature review draft
Mar 28 - Apr 1
5 days
Final literature review
Apr 4 - Apr 12
7 days
Find example RRBS data set
Apr 11 - Apr 14
Implement different classifiers and test on data
4 days
Apr 13 - Apr 19
5 days
Tranform lit. review to intro for dissertation
Apr 19 - Apr 27
Optimisation of classifiers
7 days
MSc Research Project - Plan for March/April

## Slide 2
2022
2022
Today
Week 1
2
2022
3
May 3 - May 6
4 days
Polish intro section
May 3 - May 11
Write methods section
7 days
May 3 - May 18
Implement [next steps]
12 days
MSc Research Project - Plan for May