## Slide 1
2022
2022
Today
Week 1
2
3
2022
4
5 days
Mar 14 - Mar 18
Literature research & lit. review skeleton
Mar 18 - Mar 25
6 days
Literature review draft
Mar 28 - Apr 1
5 days
Final literature review
Mar 28 - Mar 29
2 days
Find example RRBS data set
Mar 30 - Apr 7
Implement different classifiers and test on data
7 days
MSc Research Project - Plan for first month